## Wedding Day
NAME OF CLIENT OR EVENT
DATE OF EVENT |  | YOUR LOGO HERE OR COMPANY NAME
LOCATION OF EVENT |  | YOUR CONTACT DETAILS
This column you put the time | This column you put the action | This column you put the supplier | This column is for your notes, suppliers contact details, etc
Running Order | Action | Supplier | Details
10.00 AM | Hair and Make up to start | Name of suppliers | Telephone numbers, details of how many are having hair and makeup, etc
11.00 AM | Catering to start set up | Name of catering company and anyone else involved in the set up
11.30 AM | Florist to arrive | Name of florist | Details of work being done
11.30 AM | Lighting and staging to arrive to set up | Name of suppliers | This can be a lot more complicated if a large event often starting the day before or early in the morning
I will go into more details after this as you can see the timings need to be exact and can be much more complicated as this example when setting up if doing a larger event often starting the day before. The set up can be just as detailed but it gives you a good idea of how events need to be planned
2.30 PM | Photo and video to arrive | Photographer | Photographers usually do an 8 hour day, therefore their leaving time will be at 10.30 PM which works with this timings as it covers the main parts of the day including an hour of the party.
3.30 PM | Photographer to photograph grooms party | Photographer
16:00 | Bride to be ready and in dress | Hair and make up suppliers
4.00 PM | Photographer to photograph bridal party | Photographer
4.15 PM | Celebrant to arrive | Celebrant
4.30 PM | Hair and make up to finish, check veil, etc last minute lipstick | Hair and make up suppliers
4.30 PM | Grooms party and family ready to greet guests | Photographer
4.35 PM | Music to start | Ceremony musicians to start music ready for guest seating
4.45 PM | Guests to be seated | Wedding planner
4.50 PM | Grooms party to move to the front by the ceremony area | Wedding planner
4.55 PM | Bridal party assembled ready for procession | Wedding planner
4.58 PM | Bridal procession music to start | Musician
5.00 PM | Bridal entrance | Wedding planner
5.20 PM | Catering to be ready for cocktail hour | Catering company
5.20 PM | Cocktail hour music to be ready | Musicians
5.30 PM | Ceremony to finish | Celebrant
5.30 PM | Cocktail hour to start | Catering company
6.30 PM | Cocktail hour to finish | Catering company
6.35 PM | Guests to be directed to their seats | Wedding planner
6.40 PM | Drinks on tables to start being served | Catering company
6.45 PM | All guests should be seated | Wedding planner
6.50 PM | Speeches to start | Wedding party | As the planner you need to check microphones are ready and have a detailed list of who is doing speeches and how long they will last for. Crucial for the catering
7.15 PM | Dinner service to start | Catering company
7.45 PM | Starters to be cleared | Catering company
7.50 PM | Maybe another speech | Wedding party
7.55 PM | Mains to be served | Catering company
8.45 PM | Mains to be cleared | Catering company
8.45 PM | Bride and Groom to have a 10 minute photo session | Photographer | This is usually timed around the sunset for the 'golden light' shots so always check the sunset times and work this in.
8.50 PM | Dessert and coffees to be served | Catering company
9.00 PM | DJ and or musicians to be ready | Wedding planner | To prepare for first dance
9.15 PM | Dinner service to finish | Catering company | The average wedding a dinner service will last 2 hours
9.20 PM | Cutting of the cake | Wedding planner and couple | This time can vary if the cake is to be served as the dessert then it will be done earlier
9.15 PM | After dinner bar to open | Catering company
9.25 PM | First dance | Wedding couple | Often the couple may want to freshen up and pop to the bathroom so check with them just as dinner service is ending and let the DJ, musicians know wnen to start
9.30 PM | Party starts
10.00 PM | Band to start | Band if booked | Bands usually play 2 x 45 minute sets
10.30 PM | Photo and video to leave | Photographer | is will be ordered
10.45 PM | Band to break and DJ to kick back in
11.30 PM | Midnight snacks to be bought out | Catering company
11.30 PM | Second band set | Band if booked
12.00 PM | First coach or shuttle for guests to depart | Wedding planner
12.15 AM | Second band set to finish | Band if booked
12.15 AM | DJ to kick back in
12.30 AM | Shuttle for guests until 1.30 AM |  | This really varies according to what has been organised, some weddings the guests will be at the hotel, no transport will be necessary or ta
1.30 AM | Bar to close | Catering company
1.30 AM | DJ to finish | DJ
2.00 AM | Last guests to leave and break down starts | Wedding planner and suppliers